CAPSTONE PROJECT REPORT

Report 2 – Project Management Plan

– HCM, October 2026 –

Table of Contents

I. Record of Changes 	2

II. Project Management Plan 	2

1. Overview 	3

1.1 Scope & Estimation 	3

1.2 Project Objectives 	4

1.3 Project Risks 	5

2. Management Approach 	6

2.1 Project Process 	7

2.2 Quality Management 	7

2.3 Training Plan 	8

3. Project Deliverables 	8

4. Responsibility Assignments 	9

5. Project Communications 	10

6. Configuration Management 	11

6.1 Document Management 	11

6.2 Source Code Management 	11

6.3 Tools & Infrastructures 	11

# I. Record of Changes

| Date | A* M, D | In charge | Change Description |
| --- | --- | --- | --- |
| 08/09/2026 | A | CongNPT | Initialized Report 2 |
| 08/09/2026 | A | CongNPT | AddedManagement Approach, Project Deliverables, Responsibility Assignments, Project Communications, and Configuration Management |
| 10/10/2026 | M | CongNPT | Updated plan to the revised scope: WBS and effort, objectives, risks, quality scenarios, training, deliverables and tools aligned with the official tech stack |

*A - Added M - Modified D - Deleted

# II. Project Management Plan

## 1. Overview

### 1.1 Scope & Estimation

| # | WBS Item | Complexity | Est. Effort (man-days) |
| --- | --- | --- | --- |
| 1 | Account and Master Data Module |  | 16 |
| 1.1 | Account Creation, Bulk Import & Google Linking | Medium | 7 |
| 1.2 | Roles, Account Status & Account Dashboard | Simple | 4 |
| 1.3 | Terms, Faculties, Subjects & Support Categories | Medium | 5 |
| 2 | Consent and Data Protection Module |  | 27 |
| 2.1 | Indicators, Data Attributes & Consent Purposes | Complex | 8 |
| 2.2 | Purpose-Based Access Policy & Access Log | Complex | 10 |
| 2.3 | Emergency Access & Cryptographic Erasure | Complex | 9 |
| 3 | Support Request and Case Matching Module |  | 17 |
| 3.1 | Support Request Form & Data Sharing | Medium | 6 |
| 3.2 | Manual Case Matching & Contact Notification | Medium | 6 |
| 3.3 | Assignment Changes & Escalation Handling | Medium | 5 |
| 4 | Advisor Workspace and Case Management Module |  | 25 |
| 4.1 | Case List & Student Profile with Provenance | Complex | 8 |
| 4.2 | Case Notes, Stages & Referrals | Complex | 9 |
| 4.3 | Indicator Outreach, Point-in-Time View & Consent Requests | Complex | 8 |
| 5 | Welfare Support Module |  | 14 |
| 5.1 | Referral Intake & Triage | Simple | 4 |
| 5.2 | Interventions & Support Grants | Medium | 5 |
| 5.3 | External Referrals & Escalation | Medium | 5 |
| 6 | Student Self-Service Module |  | 16 |
| 6.1 | Case Tracking & Profile View | Medium | 5 |
| 6.2 | Consent Management & Access History | Complex | 7 |
| 6.3 | JSON Export & Correction Requests | Simple | 4 |
| 7 | Data Import, Reporting and Shared Services Module |  | 19 |
| 7.1 | Indicator Data Import (Excel/CSV/Google Sheet) | Medium | 6 |
| 7.2 | Case Reports & Export | Medium | 5 |
| 7.3 | Sign-in, Email Notifications, Bilingual UI & Settings | Medium | 8 |
| Total Estimated Effort (man-days) |  |  | 134 |

### 1.2 Project Objectives

Overall Objective

The objective of the AdviseCare project is to develop a web-based academic advising and student welfare management platform that matches each student's support request to a suitable advisor and tracks the case from request to closure. The system enables students to ask for academic or wellbeing support and choose which of their data to share, lets the Programme Head match cases to Academic Advisors (general or subject-specialised) or Wellbeing Advisors, and lets advisors and the Student Welfare Officer record notes, referrals and financial support, while every access to student data is decided by role, purpose and the student's consent.

The current project scope focuses on the core of supporting students and advisors — account onboarding, support requests, manual case matching, case tracking, consent management and reporting — demonstrated on a synthetic cohort of students. The architecture keeps scheduled data ingestion, automated matching and in-app scheduling as later extensions rather than part of the current version.

Quality Objectives

| # | Testing Stage | Test Coverage | No. of Defects | % of Defect | Notes |
| --- | --- | --- | --- | --- | --- |
| 1 | Requirements & Design Review | 100% | N/A | N/A | Review all requirements, ERD, consent/access-control model and UI prototype before implementation |
| 2 | Unit Test | ≥85% | ≤20 Minor | ≤5% Critical | Backend services, access policy decision point, import validation, utility classes |
| 3 | Integration Test | 100% of module interfaces | ≤15 | ≤3% Critical | Frontend–Backend–Google Sign-In–Email integration |
| 4 | System Test | 100% Functional Requirements | ≤10 | ≤2% Critical | Complete end-to-end workflow |
| 5 | Acceptance Test | 100% Major Features | ≤5 | 0% Critical | Conducted with supervisors and representative users |

Milestone Timeliness

Target: ≥95% of planned milestones completed on schedule.

Allocated Effort

| # | Activity | Percentage | Effort (MD) |
| --- | --- | --- | --- |
| 1 | Requirements Analysis | 10% | 13 |
| 2 | System & Data Model Design (ERD, Consent Model, API) | 16% | 21 |
| 3 | Backend & Consent/Access Control Development | 30% | 40 |
| 4 | Frontend Development (Student, Advisor & Staff Portals) | 22% | 30 |
| 5 | Testing & Bug Fixing | 12% | 16 |
| 6 | Documentation & Project Management | 10% | 14 |

### 1.3 Project Risks

| # | Risk Description | Impact | Possibility | Response Plans |
| --- | --- | --- | --- | --- |
| 1 | Scope keeps changing after reviewer and mentor feedback (actors, workflows, data model), causing rework. | High | High | Freeze scope per milestone; keep the ERD, functional requirements and workflows as controlled documents; agree changes with the supervisor before adopting them. |
| 2 | Per-attribute encryption and cryptographic erasure (envelope encryption, key handling) are complex to get right. | High | Medium | Use a simple envelope-encryption design (per-attribute keys wrapped by a master key in configuration); run a security design review before implementation. |
| 3 | The school provides no data source or API for FAP/FLM/LMS, so indicator data is limited to manual file imports. | Medium | High | Support Excel/CSV/Google Sheet imports with strict all-or-nothing validation; prepare synthetic datasets for every demo scenario. |
| 4 | History (point-in-time) data is accidentally updated, breaking the record of what an advisor saw on a given date. | High | Medium | Expose create-read-delete only APIs for history tables; add a code-review checklist item and tests for point-in-time reconstruction. |
| 5 | Access policy errors leak sensitive attributes across an unintended purpose. | High | Low | Peer-review the policy decision point logic; write consent/access unit tests before advisor UI work begins. |
| 6 | Google sign-in setup or email delivery fails (OAuth configuration, linking emails landing in spam). | Medium | Medium | Set up Google OAuth and the email service early; test with real personal Gmail accounts; provide a resend option for linking emails. |
| 7 | The limited number of advisors makes manual matching by the Programme Head a bottleneck. | Medium | Medium | Show advisor workload and specialisation on the matching screen; keep the design ready for automated matching later. |
| 8 | Team members become unavailable due to academic workload. | Medium | Medium | Cross-train team members across work packages and maintain updated project documentation. |
| 9 | Third-party service outages (GitHub, Render/MonsterASP hosting, Microsoft SQL Server, email service). | Medium | Low | Maintain local backups and deployment alternatives. |

## 2. Management Approach

The project adopts an Agile Scrum development methodology to support iterative implementation, continuous stakeholder feedback, and incremental delivery of software modules. Since the platform combines student support requests, manual case matching, case tracking and a consent and access control layer across student, advisor, welfare and administration portals, Agile allows each work package to evolve independently while remaining synchronized through well-defined API contracts.

Development is organized into two-week sprints. Each sprint begins with Sprint Planning, followed by implementation, daily progress tracking, code reviews, testing, and Sprint Review. Features are prioritized according to business value and technical dependency. High-risk parts such as the consent and access control layer, cryptographic erasure and the history data behind point-in-time views are developed early and incrementally with frequent integration testing, since they are hard to add later.

GitHub is used for source control following the Git Flow branching strategy, while GitHub Projects is used to manage sprint backlogs, tasks, defects, and milestone tracking. Technical documentation, ERDs, and software artifacts are maintained throughout the project to ensure traceability between requirements, design, implementation, and testing.

### 2.1 Project Process

The project follows an iterative Agile Scrum lifecycle consisting of requirement analysis, system design, sprint planning, implementation, testing, and review. Every sprint produces a potentially deployable software increment, allowing stakeholders to evaluate progress and provide feedback throughout development.

### 2.2 Quality Management

Defect Prevention

- Adopt coding standards and naming conventions.

- Define architecture before implementation.

- Maintain traceability between requirements and implementation.

- Review database and API designs before coding.

Requirements Review

- Conduct peer reviews for all project documents.

- Validate ERD, Context Diagram, SRS and UI prototypes with supervisors.

- Review feature implementation against Report 1 scope.

Code Review

- All Pull Requests require at least one reviewer.

- Verify coding standards and business logic.

- Ensure consistency between backend APIs and the consent/access-control rules.

Unit Testing

- Test backend services individually.

- Test authentication, consent policy evaluation, and point-in-time query logic.

- Verify import validation and case matching rules independently.

Integration Testing

Validate interactions among:

- Web Frontend ↔ Backend API

- Backend ↔ Microsoft SQL Server

- Backend ↔ Google Sign-In & Email Service

- Backend ↔ Encryption / Key Store

System Testing

Perform complete end-to-end scenarios including:

- Admin bulk-imports accounts and students link their personal Google accounts

- Student submits a support request and shares chosen data attributes

- Programme head matches the case and the student receives the advisor's contact information

- Advisor records notes, advances the case and refers money matters to the welfare officer

- Student withdraws consent and the steward executes erasure

- Programme head exports a case report for a time range

User Acceptance Testing

Conduct acceptance testing with supervisors and representative users to verify that all major functional requirements defined in Report 1 are fully implemented.

### 2.3 Training Plan

| Training Area | Participants | When, Duration | Waiver Criteria |
| --- | --- | --- | --- |
| History / Point-in-Time Data Modelling & Microsoft SQL Server | Entire Team | Week 1 (2 days) | Mandatory |
| Purpose-Based Access Control & Cryptographic Erasure (AES-GCM, Envelope Encryption) | Security / Backend Developers | Week 1 (3 days) | Mandatory |
| ASP.NET Core Security (Google OAuth2/OIDC, JWT) | Backend Developers | Week 3 (2 days) | Recommended |

## 3. Project Deliverables

| # | Deliverable | Due Date | Notes |
| --- | --- | --- | --- |
| 1 | Report 1 – Project Introduction | Week 1 | Project background, vision, scope, business opportunity and major features. |
| 2 | Report 2 – Project Management Plan | Week 2 | Project planning, schedule, risks, quality management and resource allocation. |
| 3 | Software Requirements Specification (SRS) v1.0 | Week 4 | Functional requirements, non-functional requirements, use cases and business rules. |
| 4 | Software Design Document (SDD) v1.0 | Week 6 | System architecture, ERD, consent/access-control design, API design and UI prototype. |
| 5 | Iteration 1 Software Package | Week 8 | Account onboarding (bulk import, Google linking), master data, consent registry and access policy engine completed. |
| 6 | Iteration 2 Software Package | Week 10 | Support requests, manual case matching, advisor workspace and case workflow completed. |
| 7 | Iteration 3 Software Package | Week 12 | Welfare support, student self-service, indicator import, reporting and complete feature integration. |
| 8 | System Testing Report | Week 13 | Unit Testing, Integration Testing, System Testing and defect reports. |
| 9 | User Guide | Week 14 | Installation guide, administrator manual, advisor manual and student manual. |
| 10 | Final Integrated System | Week 15 | Fully integrated student support matching and tracking platform ready for pilot deployment. |
| 11 | Final Project Report | Week 15 | Complete documentation including implementation, testing results, project evaluation and future work. |

## 4. Responsibility Assignments

| Responsibility | Leader | M2 | M3 | M4 |
| --- | --- | --- | --- | --- |
| Project Planning & Tracking | [TBD] | [TBD] | [TBD] | [TBD] |
| Project Documentation (Reports, SRS, SDD, User Guide) | [TBD] | [TBD] | [TBD] | [TBD] |
| Requirements Analysis & System Design | [TBD] | [TBD] | [TBD] | [TBD] |
| ERD & Database Design | [TBD] | [TBD] | [TBD] | [TBD] |
| Frontend Development | [TBD] | [TBD] | [TBD] | [TBD] |
| Backend Development | [TBD] | [TBD] | [TBD] | [TBD] |
| Consent & Access Control Engineering | [TBD] | [TBD] | [TBD] | [TBD] |
| System Integration | [TBD] | [TBD] | [TBD] | [TBD] |
| Testing & Bug Fixing | [TBD] | [TBD] | [TBD] | [TBD] |
| Deployment & Final Demonstration | [TBD] | [TBD] | [TBD] | [TBD] |

## 5. Project Communications

| Communication Item | Who/ Target | Purpose | When, Frequency | Type, Tool, Method(s) |
| --- | --- | --- | --- | --- |
| Daily Stand-up Meeting | Entire Team | Review progress, discuss blockers, assign daily tasks | Every working day (15–30 mins) | Face-to-face / Discord |
| Weekly Sprint Review | Entire Team | Demonstrate completed features and review sprint goals | Weekly | Google Meet / Classroom Meeting |
| Supervisor Meeting | Team Leader & Supervisor | Receive feedback and validate project progress | Weekly or bi-weekly | Google Meet / Face-to-face |
| Technical Discussion | Developers | Resolve implementation issues, architecture decisions | As needed | Discord, Messenger |
| Task Management | Entire Team | Track sprint tasks, bugs and milestones | Continuous | GitHub Projects |
| Source Code Review | Developers | Review Pull Requests before merging | Every feature completion | GitHub Pull Requests |
| Documentation Review | Entire Team | Review reports, SRS, SDS and diagrams | Before each submission | Google Docs / Microsoft Word |
| Final Demonstration | Team, Supervisor, Examiners | Present completed project | Final week | Presentation & Live Demo |

## 6. Configuration Management

### 6.1 Document Management

All project documents are maintained in a centralized cloud repository using Google Drive to ensure accessibility, collaboration, and backup. Documentation includes project reports, Software Requirements Specification (SRS), Software Design Specification (SDS), meeting minutes, diagrams, test reports, and user guides.

Every document follows a version numbering convention (e.g., v0.1, v0.5, v1.0). Significant modifications are recorded in the document's Record of Changes section to maintain traceability. Before each official submission, documents undergo peer review to ensure consistency, completeness, and alignment with project requirements.

Major project artifacts — including the ERD, consent and access-control policy model, API specifications, and UI designs — are treated as controlled documents. Any modification requires agreement among team members to prevent inconsistencies between analysis, design, and implementation.

### 6.2 Source Code Management

The project uses GitHub as the centralized version control platform. Source code is organized using the Git Flow branching strategy with the following primary branches:

- main – stable release version.

- develop – integration branch for completed features.

- feature/* – development of individual modules.

- hotfix/* – urgent bug fixes.

Each feature is developed in its own feature branch before being merged into the develop branch through a Pull Request. Pull Requests require at least one team member to review the implementation before approval.

Commit messages follow a consistent naming convention to improve traceability. GitHub Issues and GitHub Projects are used to manage tasks, feature requests, and software defects throughout the project lifecycle.

Database migration scripts and synthetic seed data are version-controlled alongside application code, so the schema and demonstration dataset stay reproducible across environments.

### 6.3 Tools & Infrastructures

| Category | Tools / Infrastructure |
| --- | --- |
| Security & Identity | Google Sign-In (OAuth2/OIDC) + JWT, role/purpose-based access policy engine, AES-256-GCM envelope encryption |
| Web Technology | React + TypeScript, TailwindCSS |
| Backend | ASP.NET Core Web API |
| Database | Microsoft SQL Server |
| Networking | RESTful API with OpenAPI / Swagger |
| IDEs / Editors | Visual Studio 2022, JetBrains Rider, Visual Studio Code |
| Diagramming | Draw.io, Mermaid |
| Documentation | Microsoft Word, Microsoft Excel, Google Docs |
| Version Control | Git, GitHub |
| Deployment / Hosting | Cloud container hosting (Render, MonsterASP) |
| Project Management | GitHub Projects |
| Testing Tools | xUnit, Playwright, Postman |